## 2020-21
Sl.No. | Name of Implementing Agency | Name of District | Name of Block | DMC approval Status (Y/N) | Name of CBBO allocated the block and their contact details | Focus Crop | Name of FPO | FPO registered (Y/N) | Date of FPO Registration | FPO registered under Act ( Company Act / Cooperative Act / Others please specify) | 90 days from the date of registration or 10.11.2021 | Registration No. | Date by which the FPO will achive 300 members | Appointmnet of CEO (Yes/ No) | Appointment of Accountant (Yes/ No) | No. of Farmer members | Equity Amount (in Rs.) | Whether Bank account opened | Business Plan preparation (Yes/ No) | Sanction of equity grant (Yes/ No) | If No, date by which the CBBO will submit the equity grant application | whether Applied for Equity Grant Yes/No | If Yes Date on Which Applied | If No State Reason | Equity Grant Received (Rs lakh) | Applied for Equity | Training Of CEO Yes/No | Training Of BOD Yes/No | Date of data updated/Todays Date | REMARKS/ Activity coloumn compolusary
1 | NCDC | Kadapa | Jammalamadugu | Yes | Centre for Sustainable Agriculture, Hyderabad | Spices (Turmeric), Pulses, Oilseeds | Jammalamadugu Farmers MACS (Regn. No - AMC/KDP/DCO/2021/2830) | Yes | 11.08.2021 | AP MACS Act 1995 | 10.02.2022 | AMC/KDP/DCO/2021/2830 | - | Yes | Yes | 167 | 167000 | Yes | No | No | 10.06.2022 | No | - | Farmers mobilization is going on to achieve 300 membership |  | No | No | No | 27.01.2023 | Mobilisation of Farmers is going on for achieving 300 membership
2 | NCDC | Kadapa | Pulivendula | Yes | Centre for Sustainable Agriculture, Hyderabad | Spices (Turmeric), Pulses, Oilseeds | Pulivendula Prakruthi Vyavasaya Uthpattidarula Sahakara Marketing Sangam Ltd. | Yes | 21.09.2022 | AP Coop Act 1964 | - | 654/2022 | - | No | No | 15 | 15000 | Yes | No | No | - | No | - | Farmers mobilization is going on to achieve 300 membership |  | - | No | No | 27.01.2023 | Mobilisation of Farmers is going on.
3 | NCDC | Kadapa | Vempalli | Yes | Centre for Sustainable Agriculture, Hyderabad | Spices (Turmeric), Pulses, Oilseeds | Vempalli Prakruthi Vyavasaya Uthpattidarula Sahakara Marketing Sangam Ltd. | Yes | 21.09.2022 | AP Coop Act 1964 | - | 656/2022 | - | No | No | 10 | 10000 | Yes | No | No | - | No | - | Farmers mobilization is going on to achieve 300 membership |  | - | No | No | 27.01.2023 | Mobilisation of Farmers is going on.
4 | NCDC | Kadapa | Proddatur | Yes | Centre for Sustainable Agriculture, Hyderabad | Spices (Turmeric), Pulses, Oilseeds | Proddatur Prakruthi Vyavasaya Uthpattidarula Sahakara Marketing Sangam Ltd. | Yes | 21.09.2022 | AP Coop Act 1964 | - | 655/2022 | - | No | No | 15 | 15000 | Yes | No | No | - | No | - | Farmers mobilization is going on to achieve 300 membership |  | - | No | No | 27.01.2023 | Mobilisation of Farmers is going on.
5 | NCDC | Chittoor | V.Kota | Yes | APMAS, Hyderabad | Mango, Redgram, Ragi | Venkatagirikota Agriculture Producers' MACS (Regn No - AMC/CTR/DCO/2021/56 | Yes | 30.11.2021 | AP MACS Act 1995 | 28.02.2022 | AMC/CTR/DCO/2021/55 | Achieved | Yes | Yes | 325 | 325000 | Yes | Yes | yes | - | yes | 15-7-2022 |  | 300000 | -yes | Yes | Yes | 27.01.2023
6 | NCDC | Chittoor | Baireddy Palle | Yes | APMAS, Hyderabad | Mango, Redgram, Ragi | Nallagudarayaswamy Agriculture Producers' MACS (Regn No - AMC/CTR/DCO/2021/57 | Yes | 30.11.2021 | AP MACS Act 1995 | 28.02.2022 | AMC/CTR/DCO/2022/13 | Achieved | Yes | Yes | 310 | 310000 | Yes | Yes | yes | - | yes | 15-7-2022 |  | 312000 | -yes | Yes | Yes | 27.01.2023
7 | NCDC | Chittoor | Punganur | Yes | APMAS, Hyderabad | Mango, Redgram, Ragi | Sri Suguturu Agriculture Producers' MACS (Regn No - AMC/CTR/DCO/2021/55 | Yes | 30.11.2021 | AP MACS Act 1995 | 28.02.2022 | AMC/CTR/DCO/2021/60 | Achieved | Yes | Yes | 324 | 324000 | Yes | yes | yes | - | yes | 15-7-2022 |  | 306000 | -yes | Yes | Yes | 27.01.2023
8 | NCDC | Chittoor | Somala | Yes | APMAS, Hyderabad | Mango, Redgram, Ragi | Somala Malleswaraswamy Farmers producers MACS | yes | 27.01.2022 | AP MACS Act 1995 | 27-04-2022 | AMC/DCO/CTR /2022/05 | Achieved | Yes | Yes | 305 | 305000 | Yes | Yes | yes | - | yes | 15-7-2022 |  | 305000 | -yes | Yes | Yes | 27.01.2023
9 | NCDC | Chittoor | Vijaya Puram | Yes | APMAS, Hyderabad | Mango, Redgram, Ragi | Vijayapuram Farmer Producers' MACS (Regn No - AMC/CTR/DCO/2021/60) | Yes | 30.11.2021 | AP MACS Act 1995 | 28.02.2022 | AMC/CTR/DCO/2021/56 | Achieved | Yes | Yes | 318 | 318000 | Yes | Yes | yes | - | yes | 15-7-2022 |  | 301000 | -yes | Yes | Yes | 27.01.2023
10 | NCDC | Chittoor | Nagalapuram | Yes | APMAS, Hyderabad | Mango, Redgram, Ragi | Nagalapuram Farmer Producers MACS ( Regn No.AMC/CTR.DCO/2022/13) | yes | 07.02.2022 | AP MACS Act 1995 | 07.05.2022 | AMC/CTR/DCO/2021/57 | Achieved | Yes | Yes | 319 | 319000 | Yes | Yes | Yes | - | Yes | 15-7-2022 |  | 300000 | -yes | Yes | Yes | 27.01.2023
11 | NCDC | East Godavari | Sarpavaram | Yes | BREDS, Srikakulam | Coconut, Vegetables, Pulses, Millets | Charitra Vyavasaya & Anubandha Raithu Utpathidarula Coop. Society Ltd. | Yes | 13.12.2022 | AP Coop Act 1964 | - | C-1011 | - | Yes | Yes | - | - | Yes | No | No | - | No | - | Farmers mobilization is going on to achieve 300 membership |  | - | No | No | 27.01.2023
12 | NCDC | East Godavari | Ambajipeta | Yes | BREDS, Srikakulam | Coconut, Vegetables, Pulses, Millets | Ambajipeta Agricultural and Allied Farmers Producers Cooperative Society Ltd. | Yes | 19.12.2022 | AP Coop Act 1964 | - | X 948 | - | Yes | Yes | - | - | Yes | No | No | - | No | - | Farmers mobilization is going on to achieve 300 membership |  | - | No | No | 27.01.2023 | -
13 | NCDC | East Godavari | Ravulapalem | Yes | BREDS, Srikakulam | Coconut, Vegetables, Pulses, Millets | Pragathi Vyavasaya Mariyu Anubandha Raithu Uthpathidaarula Sahakaara Sanghamu Ltd. | Yes | 19.12.2022 | AP Coop Act 1964 | - | X 947 | - | Yes | No | - | - | Yes | No | No | - | No | - | Farmers mobilization is going on to achieve 300 membership |  | - | No | No | 27.01.2023 | -
14 | NCDC | East Godavari | Kadiyam | Yes | ARTS, Srikakulam | Coconut, Vegetables, Pulses, Millets | Kadiam Yuva Rythu Vyavasaaya Mariyu Anubhanda Farmer Producers Cooperative Society Ltd. | Yes | 28.12.2022 | AP Coop Act 1964 |  | E.2 | - | Yes | Yes | - | - | Yes | No | No | - | No | - | Farmers mobilization is going on to achieve 300 membership |  | - | No | No | 27.01.2023 | -
15 | NCDC | East Godavari | Jaggampeta | Yes | ARTS, Srikakulam | Coconut, Vegetables, Pulses, Millets | Godavari Raithu Kranthi Agricultural and Allied Producers Cooperative Society Ltd. | Yes | 01.12.2022 | AP Coop Act 1964 | - | ER 414 | - | Yes | Yes | - | - | Yes | No | No | - | No | - | Farmers mobilization is going on to achieve 300 membership |  | - | No | No | 27.01.2023 | -
16 | NCDC | East Godavari | Gokavaram | Yes | ARTS, Srikakulam | Coconut, Vegetables, Pulses, Millets | Grama Sampathi Rythu Vyavasaaya Mariyu Anubhanda Farmer Producers Cooperative Society Ltd. | Yes | 26.12.2022 | AP Coop Act 1964 | - | E.1 | - | Yes | Yes | - | - | Yes | No | No | - | No | - | Farmers mobilization is going on to achieve 300 membership |  | - | Yes | Yes | 27.01.2023 | -
17 | NCDC | Kurnool | Madhavaram | Yes | EFFORT, Prakasam | Pulses, Vegetables, Oilseeds | Krushi Farmers Producers Cooperative Society Ltd. | Yes | 12.01.2023 | AP Coop Act 1964 | - | F.No.02/2023 | - | Yes | Yes | - | - | Yes | No | No | - | No | - | Farmers mobilization is going on to achieve 300 membership |  | - | No | No | 27.01.2023 | -
18 | NCDC | Kurnool | Gosepadu | Yes | EFFORT, Prakasam | Pulses, Vegetables, Oilseeds | NA | No | - | - | - | - | - | No | No | - | - | No | No | No | - | No | - | Farmers mobilization is going on to achieve 300 membership |  | - | No | No | 27.01.2023 | -
19 | NCDC | Kurnool | Gonegandla | Yes | EFFORT, Prakasam | Pulses, Vegetables, Oilseeds | The Pragathi Farmers Producers Cooperative Society Ltd. | Yes | 07.01.2023 | AP Coop Act 1964 | - | F.No.01/2023 | - | Yes | Yes | - | - | Yes | No | No | - | No | - | Farmers mobilization is going on to achieve 300 membership |  | - | No | No | 27.01.2023 | -
20 | NCDC | Kurnool | Nannuru | Yes | Nestham, Vijayawada | Pulses, Vegetables, Oilseeds | NA | No | - | - | - | - | - | No | No | - | - | No | No | No | - | No | - | Farmers mobilization is going on to achieve 300 membership |  | - | No | No | 27.01.2023 | -
21 | NCDC | Kurnool | Alluru | Yes | Nestham, Vijayawada | Pulses, Vegetables, Oilseeds | NA | No | - | - | - | - | - | No | No | - | - | No | No | No | - | No | - | Farmers mobilization is going on to achieve 300 membership |  | - | No | No | 27.01.2023 | -
22 | NCDC | Kurnool | Halagundla | Yes | Nestham, Vijayawada | Pulses, Vegetables, Oilseeds | NA | No | - | - | - | - | - | No | No | - | - | No | No | No | - | No | - | Farmers mobilization is going on to achieve 300 membership |  | - | No | No | 27.01.2023 | -
23 | NCDC | Kadapa | Rajampeta | Yes | SEARCH, Guntur | Spices (Turmeric), Pulses, Oilseeds | The Rajampet Farmer Producer Cooperative Society Ltd. | Yes | 11.11.2022 | AP Coop Act 1964 | - | 285/2022 | - | Yes | Yes | 95 | - | Yes | Yes | No | - | No | - | Farmers mobilization is going on to achieve 300 membership |  | NO | Yes | Yes | 27.01.2023 | -
24 | NCDC | Kadapa | Mydukuru | Yes | SEARCH, Guntur | Spices (Turmeric), Pulses, Oilseeds | Mydukur Raithu Uthpattidarula Sahakara Sangam Ltd. | Yes | 28.10.2022 | AP Coop Act 1964 | - | 657/2022 | - | Yes | No | 100 | - | No | No | No | - | No | - | Farmers mobilization is going on to achieve 300 membership |  | NO | Yes | Yes | 27.01.2023 | -
25 | NCDC | Kadapa | Khazipet | Yes | SEARCH, Guntur | Spices (Turmeric), Pulses, Oilseeds | Harshitha Farmers Producers Mutually Aided Cooperative Society, Khajipeta | Yes | 28.12.2021 | AP MACS Act 1995 | 28.03.2022 | AMC/KDP/DCO/2021/2837 | 31.05.2022 | Yes | Yes | 210 | 210000 | Yes | No | No | 30.06.2022 | No | - | Farmers mobilization is going on to achieve 300 membership |  | NO | Yes | Yes | 27.01.2023 | -
26 | NCDC | Kadapa | Koduru | Yes | SEARCH, Guntur | Spices (Turmeric), Pulses, Oilseeds | Saffala Kodur Producers Cooperative Society Ltd., Kodur | Yes | 30.11.2022 | AP Coop Act 1964 | - | CRA No.286 | - | Yes | No | 75 | - | No | No | No | - | No | - | Farmers mobilization is going on to achieve 300 membership |  | NO | No | No | 27.01.2023 | -
27 | NCDC | Chittoor | B.N Kandriga | Yes | SEARCH, Guntur | Ragi, Redgram, Mango | The Padmavathi Farmer Producer Cooperative Society Ltd., B.N. Kandriga | Yes | 02.12.2022 | AP Coop Act 1964 | - | 910 | - | Yes | No | 70 | - | No | No | No | - | No | - | Farmers mobilization is going on to achieve 300 membership |  | NO | No | No | 27.01.2023 | -
28 | NCDC | Chittoor | Varadaiahpalem | Yes | SEARCH, Guntur | Ragi, Redgram, Mango | The Varadaaya Farmer Producer Cooperative Society Ltd., Varadaiahpalem | Yes | 02.12.2022 | AP Coop Act 1964 | - | 911 | - | Yes | No | 55 | - | No | No | No | - | No | - | Farmers mobilization is going on to achieve 300 membership |  | NO | No | No | 27.01.2023 | -
29 | NCDC | East Godavari | Karapa | Yes | ICAR-ATARI-KVK East Godavari | Coconut, Vegetables, Pulses, Millets | Shresta Green Farms Raithu Uthpathidarula Paraspara Sahayaka Sahakara Sangham Limited | Yes | 20.12.2021 | AP MACS Act 1995 | 20.03.2022 | AMC/EGDT/DCO/2021/48 | Achieved | Yes | Yes | 386 | 772000 | Yes | Yes | Yes | Submitted | Yes | 2022-07-05 | — | 772000 | Yes | Yes | Yes | 27.01.2023
30 | NCDC | East Godavari | Panduru | Yes | ICAR-ATARI-KVK East Godavari | Coconut, Vegetables, Pulses, Millets | Mythri Raithu Utpathidarula Paraspara Sahayaka Sahakara Sangham Limited | Yes | 20.12.2021 | AP MACS Act 1995 | 20.03.2022 | AMC/EGDT/DCO/2021/49 | Achieved | Yes | Yes | 414 | 828000 | Yes | Yes | Yes | Submitted | Yes | 2022-07-05 | — | 828000 | Yes | Yes | Yes | 27.01.2023
31 | NCDC | Kurnool | Maddikera | Yes | ICAR-KVK Kurnool | Pulses, Vegetables, Oilseeds | Shri Laxmi Narasimha Swami Farmers' Producers' MACS Limited, Madikera | Yes | 20.12.2021 | AP MACS Act 1995 | 20.03.2022 | AMC/KNL/DCO/2021/4325 | Achieved | Yes | Yes | 325 | 357500 | Yes | Yes | Yes | 31.05.2022 | Yes | 31.05.2022 | - | 325000 | No | Yes | Yes | 27.01.2023
32 | NCDC | Kurnool | Pathikonda | Yes | ICAR-KVK Kurnool | Pulses, Vegetables, Oilseeds | Sevalal Farmers' Producers' MACS Limited, Pathikonda | Yes | 20.12.2021 | AP MACS Act 1995 | 20.03.2022 | AMC/KNL/DCO/2021/4326 | 31.05.2022 | Yes | Yes | 225 | 247500 | Yes | Yes | Yes | 06.06.2022 | Yes | 31.05.2022 | - | 300000 | No | No | No | 27.01.2023
33 | NCDC | Anantapur (Organic) | Khairevu | NA | Accion Fraterna Ecology Centre, Ananthapur | Groundnut, Vegetables | Sree Anjaneyaswami Sendriya Vyavasaya Raithu Utpathidarula Paraspara Sahayaka Sahakara Sangam Ltd., Khairevu (Regn.No AMC/ATP/DCO/2021/5035) | Yes | 20.10.2021 | AP MACS Act 1995 | 10.02.2022 | AMC/ATP/DCO/2021/5035 | Achieved | Yes | Yes | 383 | 383000 | Yes | Yes | Yes |  | Yes | 2022-06-06 | - | 306000 | Yes | Yes | Yes | 27.01.2023
34 | NCDC | Krishna (Organic) | Vadlamanu | NA | Centre for Sustainable Agriculture, Hyderabad | Paddy, Vegetables, Mango | Manabhoomi Prakurthi Vyavasaya Vuthpatidarula Mutually Aidied Coop. Marketing Society Ltd., Vadlamanu | Yes | 25.11.2021 | AP Coop Act 1964 | 25.02.2022 | AMC/KNA/DCO/2021/95 | 31.05.2022 | Yes | Yes | 160 | 160000 | Yes | No | No | 10.06.2022 | No |  | Farmers mobilization is going on to achieve 300 membership |  |  | No | No | 27.01.2023
35 | NCDC | Prakasam | Pasupugollu | NA | ASSIST | Red Gram, Sweet Orange | Pasupugullu Cluster Agriculture and Allied Farmers Producers Coop. Society Ltd. | Yes | 19.09.2022 | AP Coop Act 1964 | - | J-678 | - | Yes | Yes | 312 | 312000 | Yes | Yes | Yes | - | Yes | 10.10.2022 | - |  |  | Yes | Yes | 27.01.2023
36 | NCDC | SPSRNellore | Maddurapadu | NA | ASSIST | Paddy, Mango, Vegetables | Madhurapadu Agriculture and Allied Farmers Producers Coop. Society Ltd. | Yes | 20.09.2022 | AP Coop Act 1964 | - | N-672 | - | Yes | Yes | 286 | 286000 | Yes | No | No | - | No |  | Farmers mobilization is going on to achieve 300 membership | 499500 |  | Yes | Yes | 27.01.2023
37 | NCDC | Chittor | Kuppambaduru | NA | ASSIST | Mango, Redgram, Ragi | Real Kuppambaduru Farming Producers Cooperative Society Ltd. | Yes | 22.12.2022 | - | - | 912 | - | Yes | Yes | 52 | 52000 | Yes | No | No |  | No |  | Farmers mobilization is going on to achieve 300 membership |  |  | Yes | Yes | 27.01.2023
38 | NAFED | Ananthapur | Kanaganapalli | Y | LTG Mysore Greens | Ground Nut | Janani Matha Fed FPCL | Yes | 31-01-2022 | Companies ACT | 28-04-2022 | U01100AP2022PTC120676 | Achieved | YES | YES | 306 | 306000 | Yes | yes | No | Submitted to NAFED | Yes | 12th October |  | No |  | yes | no
39 | NAFED | Ananthapur | Ramagiri | Y | LTG Mysore Greens | Ground Nut | Shri Navya Nelamma Fed FPCL | Yes | 26-03-2022 | Companies ACT | 20-06-2022 | U01100AP2022PTC121165 | Achieved | YES | YES | 315 | 315000 | Yes | yes | No | Submitted to NAFED | Yes | 12th October |  | No |  | yes | no
40 | NAFED | Ananthapur | Tadimarri | Y | LTG Mysore Greens | Ground Nut | Pudami Thalli Fed FPCL | Yes | 28-01-2022 | Companies ACT | 20-04-2022 | U01100AP2022PTC120645 | Achieved | YES | YES | 308 | 308000 | Yes | yes | No | Submitted to NAFED | Yes | 15th November |  | No |  | yes | no
41 | NAFED | Ananthapur | Narpala | Y | LTG Mysore Greens | Ground Nut | Bhoo Janani Fed FPCL | Yes | 31-01-2022 | Companies ACT | 25-04-2022 | U01100AP2022PTC120675 | Achieved | YES | YES | 302 | 302000 | Yes | yes | No | Submitted to NAFED | Yes | 15th November |  | No |  | yes | no
42 | NAFED | Ananthapur | Bukkaraya Samudram | Y | LTG Mysore Greens | Ground Nut | Avani Matha Fed FPCL | Yes | 2022-11-02 | Companies ACT | 2022-05-05 | U01119AP2022PTC120811 | Achieved | YES | YES | 310 | 310000 | Yes | yes | No | Submitted to NAFED | Yes | 2023-12-18 |  | No |  | yes | no
43 | NAFED | West Godavari | Bhimadolu | NA | Access Develoment Services | Oil Palm | Nandagopal palm oilfed Producer Company Limited | Yes | 15/04/2021 | COMPANY ACT | 2022-02-07 | U01110AP2021PTC118014 | ACHIVED | YES | YES | 336 | 5,00,000 | Yes | Yes | No | 2022-12-09 | YES | 2022-12-09 | Submitted | No | Yes | Yes | Yes | 21/12/2022
44 | NAFED | West Godavari | Deverapalli | NA | Access Develoment Services | Oil Palm | Laxmi Ganapati palm oilfed producer Company Limited | Yes | 2021-04-05 | COMPANY ACT | 2022-02-07 | U01100AP2021PTC117920 | ACHIVED | YES | YES | 300 | 10,00,000 | Yes | Yes | Yes | YES | YES | 2023-09-01 |  | 500000 | Yes | Yes | Yes | 21/12/2022
45 | NAFED | West Godavari | Dwaraka Tirumula | NA | Access Develoment Services | Oil Palm | Venkateswara palm oilfed producer Company Limited | YES | 26/03/2021 | COMPANY ACT | 2022-02-07 | U01400AP2021PTC117862 | ACHIVED | YES | YES | 300 | 10,00,000 | Yes | Yes | Yes | YES | YES | 2023-11-21 |  | 500000 | Yes | Yes | Yes | 21/12/2022
46 | NAFED | West Godavari | Dwaraka Tirumula | NA | Access Develoment Services | Oil Palm | Dwaraka Palm oilfed Producer Company Limited | YES | 2021-04-05 | COMPANY ACT | 2022-02-07 | U01100AP2021PTC117919 | ACHIVED | YES | YES | 300 | 6,00,000 | Yes | Yes | Yes | YES | YES | April.2022 |  | 300000 | Yes | Yes | Yes | 21/12/2022
47 | NAFED | West Godavari | Nallajerlla | NA | Access Develoment Services | Oil Palm | Godavari Palm oilfed Producer Company Limited | YES | 14/05/2021 | COMPANY ACT | 2022-02-07 | U01404AP2021PTC118251 | ACHIVED | YES | YES | 315 | 6,40,000 | Yes | Yes | Yes | YES | YES | 2021-05-01 |  | 320000 | Yes | Yes | Yes | 21/12/2022
48 | NAFED | Chittoor | Santhipuram | yes | The Institute of Entrepreneurship Development (IED) | Pomegranate, baby corn, sweet corn, banana, potato, tomato, chillies | AGROTIS FED FARMER PRODUCER COMPANY LTD | Yes | 07.01.22 | Company Act | ####### | U0110000AP2022PTC120506 | 29.04.22 | Yes | yes | 100 | 20000 | Yes | No | No | ####### | No | No |  | No | Yes | YES | 28.01.2022,10.02.2022
49 | NAFED | Anantapuramu | Battalapalli | NA | Grant Thornton Bharat LLP | Groundnut | Bathalapalli FED Farmer Producer Company Limited | Y | 26-03-2021 | Company Act |  | U01100AP2021PTC117864 | Achieved | Y | Y | 653 | 1305000 | Y | Y | Y | NA | Y | Aug'2021 | NA | 300000 | Yes | Yes | Yes | 23.12.2022
50 | NAFED | Anantapuramu | Mudigubba | NA | Grant Thornton Bharat LLP | Groundnut | Sri Lakshmi Narashimha Swamy Mudigubba FED Farmer Producer Company Limited | Y | 2021-06-29 | Company Act |  | U01400AP2021PTC118671 | Achieved | Y | Y | 302 | 302000 | Y | Y | Y | NA | Y | Feb'22 |  | 300000 | Yes | Yes | Yes | 23.12.2022
51 | NAFED | Anantapuramu | Raptadu | NA | Grant Thornton Bharat LLP | F & V | Raptadu FED Farmer Producer Company Limited | Y | 25-03-2021 | Company Act |  | U01100AP2021PTC117846 | Achieved | Y | Y | 333 | 333000 | Y | Y | Y | NA | Y | Apr'22 |  | 300000 | Yes | Yes | Yes | 23.12.2022
52 | NAFED | Anantapuramu | Rajanagaram | NA | Grant Thornton Bharat LLP | Oil Palm | Rajanagaram FED Farmer Producer Company Limited | Y | 26-03-2021 | Company Act |  | U01100AP2021PTC117866 | Achieved | Y | Y | 300 | 300000 | Y | Y | Y | NA | Y | Sept'21 |  | 300000 | Yes | Yes | Yes | 23.12.2022
53 | NABARD | Anantpur | Kalagalla Village (Kuderu Mandal) | 12.08.2020 & 09.07.2021 & 19.11.2021 | Accion Fraterna Ecology Centre | Groundnut & Horticulture | Srama Jeevana Raithula Paraspara Sahayaka Sahakara Sangam Ltd, | Registered | 20-10-2021 | Andhra Pradesh MACS Act 1995 | 2022-10-02 | AMC/ATP/DCO/2021/5034 | Achieved | Yes | Yes | 416 | 457600 | Yes | Yes | Yes | Submitted | Yes | 19th April 2022 |  | 366000 |  | Yes | Yes | 23.12.2022
54 | NABARD | Chittoor | B. Kothkotha | 14.08.2020 & 21.10.2020 & 02.07.2021 | Mahila Abhivruddhi Society (APMAS) | Tomato | Horsley Hills Farmers Producer Company Limited,Vinayak Reddy -9440800622 | Registered | 21-07-2021 | Company Act | 2022-10-02 | U01100AP2021PTC118896 | achieved | Yes | yes | 411 | 411000 | Yes | yes | Yes |  | yes | 2022-06-01 |  | 307000 | yes | yes | yes | 23.12.2022
55 | NABARD | Chittoor | Kalakada |  | Mahila Abhivruddhi Society (APMAS) | Tomato | Reddamma Farmer Producers Company Limited, | Registered | 27-07-2021 | Company Act | 2022-10-02 | U01100AP2021PTC118992 | achoeved | Yes | yes | 372 | 372000 | Yes | yes | Yes |  | yes | 2022-06-01 |  | 303000 | yes | yes | yes | 23.12.2022
56 | NABARD | East Godavari | Addateegala | 10.08.2020 & 20.11.2020 & 24.03.2021 & 19.07.2021 | National Agro Foundation | Cashew Nut & Pulses | Addatheegala Somalamma Cashewnut Farmer Producer Company Limited,Sunil - 9110550127 | Registered | 2021-04-08 | Company Act | 2021-07-10 | U01100AP2021PTC119040 | Achieved | Yes | Yes | 546 | 546000 | Yes | Yes | Yes |  | Yes |  |  | 302000 |  | Yes | Yes | 19/12/2022
57 | NABARD | East Godavari | Y Ramavaram |  | National Agro Foundation | Cashew Nut & Pulses | Y Ramavaram Sri Gubbalamma Farmer Producer Company Limited, | Registered | 2021-09-07 | Company Act | 2021-06-11 | U01110AP2021PTC118783 | Achieved | Yes | Yes | 515 | 515000 | Yes | Yes | Yes |  | Yes |  |  | 3,00,000 |  | Yes | Yes | 19/12/2022
58 | NABARD | Guntur | Gurazala | Y | SEARCH | Chillies | Palnadu Chilly Farmer Producer Company Limited,Parthasaradi - 7013717747 | Registered | 17.08.2021 | Company Act | 15.11.2021 | U01400AP2021PTC119164 | 31.10.2021 | Yes | Yes | 430 | 430000 | Yes | YES | YES |  | YES | 29.10.2021 |  | 3 | YES | YES | YES | 23.12.2022
59 | NABARD | Guntur | Vinukonda | Y | SEARCH | Chillies/ Pulses | Samvrudhi Mirchi Farmer Producer Company Limited, | Registered | 10.08.2021 | Company Act | 08.11.2021 | U01100AP2021PTC119098 | 31.10.2021 | Yes | Yes | 330 | 330000 | Yes | YES | YES |  | YES | 29.10.2021 |  | 3 | YES | YES | YES
60 | NABARD | Kadapa | Rajampeta | 17.08.2020 & 31.03.2021 & 26.10.2021 | Rayaliseema Harijana Garijana Back word & Maniraty Seva Samajam(RHGBMSS) | Banana | Sri Annamaiah Farmer Producer Mutually Aided Cooperative Society Limited,Ratnam - 9848061373 | Registered | 06.08.2021 | Cooperative Act | Yes | AMC/KDP/DCO/2021/2829 | 328 | Yes | Yes | 328 | 328000 | Yes | Submitted | Yes | Received | Yes | 14.05.2022 |  | 328000 | Yes | Yes | Yes | 23.12.2022 | Submitted Proposal
61 | NABARD | Kadapa | SAKN |  | Rayaliseema Harijana Garijana Back word & Maniraty Seva Samajam(RHGBMSS) | Banana | Sri Avadhutha Kasinayana Farmer Producers Mutually Aided Cooperative Society Ltd, | Registered | 30.07.2021 | Cooperative Act | Yes | AMC/KDP/DCO/2021/2826 | 500 | Yes | Yes | 500 | 1000000 | Yes | Submitted | Yes | Received | Yes | 10.10.2021 |  | 350000 | Yes | Yes | Yes | 23.12.2022 | Recived Agriculture Fertilizer Licence and started input business Rs.1500000/- laks worth of Inputs busenes don
62 | NABARD | Krishna | Agiripalli | 13.08.2020 & 31.03.2021 |  | Mango | Sri Shobhanachala Vyagra Narasimha Swamy Farmers Producer Company Limited,Rambabu - 9666407287 | Registered | 2021-01-12 | Company Act | 28-02-2022 | U01119AP2021PTC120216 | 31-03-2022 | Yes | No | 300 | 185000 | Yes | No | No |  | No |  | Not mobilised 3 lakh as share capital | no |  | Yes |  | 23.12.2022
63 | NABARD | Krishna | Nuzividu |  | Centre for sustainable Agriculture | Mango | Nuzivid Horticulture Farmers Producer Company Limited, | Registered | 28-10-2021 | Company Act | 31-01-2022 | U01100AP2021PTC119881 | 31-03-2022 | Yes |  | 198 | 170000 | Yes | No | No |  | No |  | Not mobilised 3 lakh as share capital |  |  | Yes |  | 23.12.2022
64 | NABARD | Kurnool | Allagadda | 13.08.2020 & 07.07.2021 & 23.12.2021 | NABCONS | Cotton and ONION | Renati Suryachand Farmers Producer Company Limited,Kiran - 9967131920 | Registered | 17.07.2021 | Company Act | 110 DAYS | U01109AP2021PTC009033 |  | Yes |  | 330 | 330000 | Yes | Yes | yes |  | yes | 2021 | yes | Sanctioned Equity Grant | yes | yes | no | 23.12.2022
65 | NABARD | Kurnool | Yemmiganur |  | NABCONS | Onion | Yemmiganur Farmers Producer Company Limited, | Registered | 03.08.2021 | Company Act | 124DAYS | U011400AP2021PTC118860 |  | Yes | YES | 370 | 370000 | Yes | NO | YES |  |  |  |  | Sanctioned Equity Grant |  | yes | no | 23.12.2022
66 | NABARD | Nellore | Gudur | 13.08.2020 & 21.06.2021 | NABCONS | Acid Lime | Guduru Venkateswara Farmers Producer Company Limited, | Registered | 30.07.2021 | Company Act | 111DAYS | UO1100AP2021PTC118982 | submitted | Yes | YES | 302 | 302000 | Yes | Yes | Yes |  | yes | 2022 |  | 302000 | yes |  | no | 23.12.2022
67 | NABARD | Nellore | Podalkur |  | NABCONS | Acid Lime | Podalkur Farmers Producer Company Limited, | Registered | 20.07.2021 | Company Act | 130DAYS | UO1100AP2021PTC118996 |  | Yes | YES | 300 | 300000 | Yes | Yes | Yes |  | yes | 2022 |  | 300000 | yes | yes | no | 23.12.2022
68 | NABARD | Prakasam | Markapur | 17.08.2020 & 03.04.2021 & 15.12.2021 | EFFORT | Pulses | Markapuram Divya Teja Farmers Producer Company Limited,EFFORT - 9959900081 | Registered | 13.07.2021 | Company Act |  | U01100AP2021PTC118800 |  | Yes | YES | 500 | 500000 | Yes | Yes | Yes |  | Yes |  |  | Sanctioned Equity Grant | Yes | Yes |  | 23.12.2022
69 | NABARD | Prakasam | Podili |  | EFFORT | Pulses | Podili Divyajyothi Farmers Producer Company Limited, | Registered | 23.07.2021 | Company Act |  | U01110AP2021PTC118914 |  | Yes | Yes | 390 | 390000 | Yes | Yes | Yes |  | Yes |  |  | Sanctioned Equity Grant | Yes | Yes |  | 23.12.2022
70 | NABARD | Srikakulam | Ichchapuram | 22.09.2020 & 22.07.2021 & 16.12.2021 | Action in Rural Technology and Service (ARTS) | Coconut | Swechavathi Farmer Producer Company Limited,Sanyasirao - 9440630945 | Registered | 05.08.2021 | Company Act | 05.11.2021 | U01110AP2021PTC119057. | 30.12.2021 | yes | yes | 325 | 635000 | Yes | yes | Yes |  | Yes |  |  | 306000 | Yes | yes | yes | 23.12.2022
71 | NABARD | Srikakulam | Sompeta |  | Action in Rural Technology and Service (ARTS) | Coconut | Marla Polamma Farmer Producer Company Limited, | Registered | 03.11.2021 | Company Act | 2 Days | U01100AP2021PTC119318. | 30.11.2021 | Yes | yes | 305 | 610000 | Yes | yes | Yes |  | yes |  |  | 304000 | Yes | yes | yes | 23.12.2022
72 | NABARD | Visakhapatnam | Chintapalli | 14.08.2020 & 19.06.2021 & 07.12.2021 | IIMR | Turmeric,spices,millets horticultural crops | Lambasingi Tribal Products Farmers Producer Company Limited. | Registered | 2021-09-08 | Company Act |  | U01409AP2021PTC119079 | ACHIEVED | Yes | YES | 310 | 3,10,000 | Yes | yes | Yes |  | Yes |  |  | 3,10,000 |  | YES | YES | 23.12.2022 | Activities of July month 2022Awareness programmes, Millet Seed distribution Marketing linkages, Applied For GST, Designed products labeling, marketing linkages
73 | NABARD | Visakhapatnam | Paderu |  | IIMR | Turmeric,spices, millets horticultural crops | Giri Siri Tribal Farmers Producer Organization Mutually Aided Cooperative Society Limited, | Registered | 15/9/2021 | Cooperative Act |  | ADHNRPM202102 | ACHIEVED | Yes | YES | 450 | 450000 | Yes | yes | Yes |  |  |  |  | 3,00,000 |  | YES | YES | 23.12.2022 | Activities of July month Millet Seed distribution Mobilization drives, Giri Siri FPO sold custard apple 10 tonnes of custard apple worth of 8 lakh rupees, applied for FASSAI
74 | NABARD | Vizianagaram | Cheepurupalli/Gurala/Merakamudidam | 13.08.2020 & 04.01.2022 | BREDS | Pulses | Kissan Kranthi Farmers Producer Company Limited,Ramakrishnaraj - 9347346900 | Registered | 2021-04-08 | Company Act |  | U01100AP2021PTC119036 | Completed | Yes | YES | 382 | 301000 | Yes | Yes | YES | SUBMITTED | YES |  |  | 3,00,000/- | yes | Yes | Yes | 23.12.2022
75 | NABARD | Vizianagaram | Nellimarla |  | BREDS | Pulses | Subhodaya Farmers Producer Company Limited, Suman - 9493947776 | Registered | 26-07-2021 | Company Act |  | U01110AP2021PTC118924 | Completed | Yes | YES | 325 | 314000 | Yes | Yes | YES | SUBMITTED | YES | 2021-08-01 |  | 3,00,000/- | Yes | Yes | Yes | 23.12.2022
76 | NABARD | West Godavari | Devarapalli | 13.08.2020 & 10.08.2021 | ASSIST | Acid lime | Sri Pedda Patamma Farmers Producer Company Limited,M.Manoj-9966336475 | Registered | 2021-03-08 | Company Act | Yes | U01409AP2021PTC119030 | Achived | Yes | Yes | 390 | 3,90,000 | Yes | Yes | Yes | Submitted | Yes | 24-02-2022 |  | 3,00,000 | Yes | Yes | Yes | 23.12.2022 | Fertilizer licence received, Pesticides licence applied it's under process and Management Cost received
77 | NABARD | West Godavari | Kamavarapukota |  | ASSIST | Acid lime | Sri Vidyadhararao Farmers Producer Company Limited,Rangarao - 9866333896 | Registered | 29-07-2021 | Company Act | Yes | U01100AP2021PTC118977 | Achived | Yes | Yes | 378 | 3,78,000 | Yes | Yes | Yes | Submitted | Yes | 16-03-2022 |  | 3,00,000 | Yes | Yes | Yes | 23.12.2022 | Pesticides and Fertilizer licences recived and Management Cost also received
78 | NABARD | Guntur | Piduguralla, Sattenapalli, Bapatla | Y | SEARCH | Chilly | Kshethra Natural Farmer Producer Company Limited,Parthasaradi - 7013717747 | Registered | 28.08.2021 | Company Act | 28.11.2021 | U01100AP2021PTC119248 | 31.10.2021 | Yes | YES | 357 | 357000 | Yes | YES | YES |  | YES | 29.10.2021 |  | 3 | YES | YES | YES | 23.12.2022
79 | NABARD | Kadapa | Vontimetta and Nandalur | Not Applicable | Centre for Sustainable Agriculture (CSA) | Banana | Ekashila Farmers Producer Company Limited,Rambabu - 9666407287 | Registered | 2021-04-10 | Company Act | 31-12-2021 | U01110AP2021PTC119615 | 28-02-2022 | Yes | No | 302 | 303000 | Yes | Yes | Yes |  | Yes | 15.07.2022 |  | 303000 | Yes | Yes |  | 23.12.2022
80 | NABARD | Krishna | Reddigudem, A Kondur, G Kondur | Not Applicable | Centre for Sustainable Agriculture (CSA) | Mango | Druthi Krishna Farmers Producer Company Limited, | Registered | 2021-08-12 | Company Act | 2022-08-03 | U01400AP2021PTC120270 | 31-03-2022 | Yes | No | 185 | 185000 | Yes | No | No |  |  |  |  | NA |  | Yes |  | 23.12.2022
81 | NABARD | Srikakulam | Seethampeta, Veeragattam, Burja, Kothuru | yes | Action in Rural Technology and Service (ARTS) | Cashew | Pedda Gedda Farmer Producer Company Limited,Sanyasirao - 9440630945 | Registered | 03.12.2021 | Company Act | no | U01409AP2021PTC120232. |  | yes | yes | 305 | 610000 | Yes | yes | Yes |  | Yes |  |  | 310000 | Yes | yes | yes | 23.12.2022
82 | NABARD | Visakhapatnam | G Madugula | Not Applicable | Centre for Sustainable Agriculture (CSA) | Turmeric | Giri Siri Farmers Producer Company Limited,Rambabu - 9666407287 | Registered | 2021-08-11 | Company Act | 2022-08-02 | U01100AP2021PTC119939. | 28-02-2022 | Yes | No | 341 | 323000 | Yes | Completed | No | 2022-10-03 | Yes | 18th May 2022 |  | 318500 | Yes | Yes |  | 23.12.2022
83 | NABARD | Vizianagaram | Pachipenta, Salur, Makkuva, Gajapathinagaram, Merakamudidam, Cheepurapalle, Garagubilli | Yes` | Action in Rural Technology and Service (ARTS) | Mango | Adivasi Mahila Farmers Producer Company Limited,Sanyasirao - 9440630945 | Registered | 25.10.2021 | Company Act | 15 daysa | U01100AP2021PTC119844. | 25.12.2021 | yes | yes | 330 | 630000 | Yes | yes | no |  |  |  |  | no |  | yes | yes | 23.12.2022
84 | SFAC | Anantapuram (Ananatpur) | Anantapur | Approved | Grant Thornton Bharat LLP | Groundnut | Anantapur Rural Farmers producer Company Limited | Y | 2021-03-25 | Company Act |  | U01100AP2021PTC117842 | Achieved | Yes | Y | 600 | 600000 | Yes | Y | Y | NA | Y | Apr'22 |  | 300000 | Yes | Yes | Yes | 23.12.2022
85 | SFAC | Anantapuram (Ananatpur) | Guntakal | Approved | Grant Thornton Bharat LLP | Groundnut | Guntakal Farmer Producer Company Limited | Y | 2021-04-19 | Company Act |  | U01400AP2021PTC118035 | Achieved | Yes | Y | 301 | 301000 | Yes | Y | Y | NA | Y | May'22 |  | 300000 | Yes | Yes | Yes | 23.12.2022
86 | SFAC | Anantapuram (Ananatpur) | Pamidi | Approved | Grant Thornton Bharat LLP | Groundnut | Pamidi Mandal Farmers Producer Company Limited | Y | 2021-03-12 | Company Act |  | U01100AP2021PTC117669 | Achieved | Yes | Y | 304 | 304000 | Yes | Y | Y | NA | Y | Aug'21 |  | 300000 | Yes | Yes | Yes | 23.12.2022
87 | SFAC | Anantapuram (Ananatpur) | Singanamala | Approved | Grant Thornton Bharat LLP | Groundnut | Singanamala Farmer Producer Company Limited | Y | 2021-04-25 | Company Act |  | U01400AP2021PTC117975 | Achieved | Yes | Y | 302 | 302000 | Yes | Y | Y | NA | Y | May'22 |  | 300000 | Yes | Yes | Yes | 23.12.2022
88 | SFAC | Anantapuram (Ananatpur) | Vajrakarur | Approved | Grant Thornton Bharat LLP | Groundnut | Vajrakarur Farmer Producer Company Ltd. | Y | 2021-06-28 | Company Act |  | U01100AP2021PTC118661 | Achieved | Yes | Y | 304 | 304000 | Yes | Y | Y | NA | Y | Mar'22 |  | 300000 | Yes | Yes | Yes | 23.12.2022
89 | SFAC | Chittoor | Chittoor | Approved | National Agro Foundation | Groundnut and Mango | Chittor Farmer Producer Company Limited | Registered | 2021-07-23 | Company Act | 21-10-2021 | U01100AP2021PTC118912 | Completed | Yes | Yes | 501 | 501000 | Yes | Yes | No | 15/2/2022 | Yes | Applied on 21st March 2022 |  | 300000 |  | Yes | Yes | 19/12/2022
90 | SFAC | Chittoor | Shrikalahsti | Approved | National Agro Foundation | Groundnut and Vegetable | Kalahasteeswara Farmer Producer Company Limited | Registered | 2021-09-11 | Company Act |  | U01409AP2021PTC119393 | Completed | Yes | Yes | 582 | 582000 | Yes | Yes | No | 30/1/2022 | Yes | Applied on 21st March 2022 |  | 300000 |  | Yes | Yes | 19/12/2022
91 | SFAC | East Godavari | Razole | Approved | PricewaterhouseCoopers Pvt. Ltd. | Cocoa and vegetables with coconut | Kalpataruvu Coconut Farmers Producer Company Limited | Registered | 2021-07-30 | Company Act | Yes | U01100AP2021PTC118991 | Achieved | yes | yes | 340 | 340000 | Yes | yes | yes |  | yes | Applied on 23rd july 2022 |  | No | yes | yes | yes | 20/12/2022
92 | SFAC | Kurnool | Gudur | Not Required | Andhra Pradesh Mahila Abhivruddhi Society (APMAS) | Cotton, Redgram | Raithu Viswam Producer Company Limited | Registered | 2022-01-13 | Company Act |  | U01409AP2022PTC120550
93 | SFAC | Guntur | Durgi | Approved | PricewaterhouseCoopers Pvt. Ltd. | Red Chilli, Red Gram | Durgi Farmers Producer Company Limited | Registered | 2021-11-16 | Company Act | yes | U01100AP2021PTC120055 | Achieved | Yes | yes | 179 | 1,79,000 | Yes | Yes | Under process |  | No |  | in process | No | NO | Yes | Yes | 21/12/2022
94 | SFAC | Krishna | Mopidevi | Approved | PricewaterhouseCoopers Pvt. Ltd. | Vegetables | Sri Skandaya Farmers Producer Company Limited | Registered | 2021-08-16 | Company Act | Yes | U01110AP2021PTC119163 | 31-03-2022 | Yes | yes | 312 | 3,12,000 | Yes | Yes | Yes |  | Yes | Applied on 15/12/2022 |  | No | Yes | Yes | Yes | 21/12/2022
95 | SFAC | Kurnool | Pamulapadu | Approved | National Agro Foundation | Maize and Blackgram | Mana Voori Nesthalu Farmers Producer Company Limited | Registered | 2021-07-23 | Company Act | Yes | U01100AP2021PTC118916 |  | Yes | Yes | 507 | 760500 | Yes | Yes | Yes |  |  |  |  | 4,60,500 | Yes | Yes | Yes | 19/12/2022
96 | SFAC | Kurnool | Uyyalawada | Not Required | Andhra Pradesh Mahila Abhivruddhi Society (APMAS)
97 | SFAC | Nellore | Marripadu | Pending | Prathap Educational Society (PES) |  | Ranganatha Swamy Women Farmers Producer Company Ltd. | Registered | 2021-05-11 | Company Act |  | U01100AP2021PTC118210 |  |  |  | 210 | 63000
98 | SFAC | Nellore | Nellore | Pending | Prathap Educational Society (PES) |  | Sri Raja Rajeshwari Women Farmers Producer Company Ltd. | Registered | 2021-05-11 | Company Act |  | U01100AP2021PTC118215 |  |  |  | 200 | 60000
99 | SFAC | Prakasham |  | Approved | Prathap Educational Society (PES) | Pulses | Ponnaluru Women Farmer Producer Company Limited | Registered | 2021-04-22 | Company Act | 2021-07-22 | U01100AP2021PTC118074 | 2022-03-31 | Yes | Yes | 60 | 90000 | Yes | No | No | 2022-03-31 |  |  |  | NA
100 | SFAC | Srikakulam | G. Sigadam | Approved | Prathap Educational Society (PES) | Maize | G.Sigadam Women Farmers Producer Company Limited | Registered | 2021-08-27 | Company Act | 2021-11-27 | U01100AP2021PTC119245 | 2022-03-31 | Yes | Yes | 207 | 3,10,500 | Yes | No | No | 2022-03-31 |  |  |  | NA
101 | SFAC | Chittoor | Ramachandrapuram | Not Required | Andhra Pradesh Mahila Abhivruddhi Society (APMAS) | Paddy, Groundnut | Rayalacheruvu Farmers Producer Company Limited | Registered | 2021-10-09 | Company Act | 2022-10-02 | U01100AP2021PTC119685 | 28-2-22 | yes | yes | 326 | 326000 | yes | no | yes | applied | Yes |  |  | 10000 | yes | Yes | Yes | 26-8-2022 | Applied for equity grant , but received only 10000
102 | SFAC | Anantpur | Settur | Not Required | Andhra Pradesh Mahila Abhivruddhi Society (APMAS) | Groundnut, Vegetables | Nandeeswara Farmers Producer Company Limited | Registered | 2021-11-02 | Company Act |  | U01100AP2021PTC119920
103 | SFAC | West Godavari | Jangareddygudem | Approved | PricewaterhouseCoopers Pvt. Ltd. | Acid Lime | Maddi Anjaneya Farmers Producer Company Limited | Registered | 2022-05-25 | Company Act | 2022-08-23 | U01100AP2022PTC121771 |  | Yes | Yes | 245 | 245000 | Yes | Yes | No |  | No |  |  | NA | No | Yes | Yes | 20/12/2022
104 | SFAC | Y.S.R Kadapa | Sidhavatam | Approved | National Agro Foundation | Banana | Siddavatam Farmer Producer Company Limited | Registered | 2021-07-13 | Company Act |  | U01100AP2021PTC118808 | Completed | Yes | Yes | 502 | 753000 | Yes | Yes | Yes |  | Yes | 2022-07-02 |  | 457500 | 4,57,500 | Yes | Yes | 19/12/2022
105 | SFAC | Y.S.R Kadapa | Pendlimarri | Not Required | Andhra Pradesh Mahila Abhivruddhi Society (APMAS)
106 | SFAC | Y.S.R Kadapa | VN Palli | Approved | National Agro Foundation | Banana | Veerapunayunipalli Farmer Producer Company Ltd. | Registered | 2021-07-01 | Company Act | Yes | U01100AP2021PTC118699 | Completed | Yes | Yes | 516 | 774000 | Yes | Yes | No |  | Yes | 2022-07-02 |  | 456000 | 4,50,000 | Yes | Yes | 19/12/2022

## 2021-22
| Name of Implementing Agency | Name of District | Name of Block | DMC approval Status (Y/N) | Name of CBBO allocated the block and their contact details | Focus Crop | Name of FPO | FPO registered (Y/N) | FPO registered under Act ( Company Act / Cooperative Act / Others please specify) | Date of FPO Registration | Registration No. | 90 days from the date of registration or 10.11.2021 | Date by which the FPO will achive 300 members | Appointmnet of CEO (Yes/ No) | Appointment of Accountant (Yes/ No) | No. of Farmer members | whether Applied for Equity Grant Yes/No | If Yes Date on Which Applied fo EG | If No State Reason | Equity Amount (in Rs.) | Whether Bank account opened | Business Plan preparation (Yes/ No) | Sanction of equity grant (Yes/ No) | If No, date by which the CBBO will submit the equity grant application | Equity Grant Received (Rs lakh) | Training Of CEO Yes/No | Training Of BOD Yes/No | Date of data updated/Todays Date | REMARKS/ Activity coloumn compolusary
1 | SFAC | Y.S. R. Kadapa | Chinthakommadinne | Y | Ekalavya Foundation | Banana | Chinthakommadinne Farmers Producer Company Limited | YES | Company Act | 23/12/21 | U01400AP2021PTC120397 | 23.03.2022 | Completed | Yes | Yes | 300 | Yes | 07.09.2022 |  | 300000 | Yes | Yes | Yes |  | 300000 | Yes | Yes | 21.12.2022
2 | SFAC | Y.S. R. Kadapa | Pendlimarri | Y | Ekalavya Foundation | Banana and Floriculture | Pendlimarri Farmers Producer Company Limited | YES | Company Act | 30/12/21 | U01409AP2021PTC120433 | 30.03.2022 | Completed | Yes | Yes | 300 | No |  | Documents Sent for Signatures of Share Holders |  | Yes | Yes | No | 31.12.2022 |  | Yes | Yes | 21.12.2022
3 | SFAC | Y.S. R. Kadapa | Valluru | Y | Ekalavya Foundation | Pulses | Valluru Farmers Producer Company Limited | YES | Company Act | 15/12/21 | U01100AP2021PTC120319 | 15.03.2022 | Completed | Yes | Yes | 300 | Yes | 07.09.2022 |  | 300000 | Yes | Yes | Yes |  | 300000 | Yes | Yes | 21.12.2022
4 | SFAC | Y.S. R. Kadapa | Kamalapuram | Y | Ekalavya Foundation | Pulses | Kamalapuram Raithu Seva Farmers Producer Company Limited | YES | Company Act | 31/12/21 | U01100AP2021PTC120441 | 31.03.2022 | Completed | Yes | Yes | 300 | Yes | 10.10.2022 |  | 300000 | Yes | Yes | Yes |  | 300000 | Yes | Yes | 21.12.2022
5 | SFAC | Y.S. R. Kadapa | Khajipeta | Y | Ekalavya Foundation | Oilseed and Turmeric | Khajipeta Farmers Producer Company Limited | YES | Company Act | 2022-06-01 | U01100AP2022PTC120485 | 06.04.2022 | Completed | Yes | Yes | 300 | Yes | 10.10.2022 |  | 300000 | Yes | Yes | Yes |  | 300000 | Yes | Yes | 21.12.2022
6 | SFAC | Guntur | Machavaram | y | Prathap Educational Society | Red Chillies and Pulses | Pedakurapadu | yes | companies act | 29/06/2022 | U01409AP2022PTC122129 | 30/09/2022 | completed | Yes | Yes | 475 | yes | 2022-05-11 |  | 712500 | Yes | Yes | not received |  |  | yes | yes | 22/12/2022
7 | SFAC | Guntur | Dachepalle | y | Prathap Educational Society | Red Chillies and Pulses | Dachepalli | yes | companies act | 2022-06-12 | U011AP2022PTC123454 | 2023-07-03 |  | Yes | Yes | 75 | No | [10 empty] | 22/12/2023
8 | SFAC | Guntur | Pedakurapadu | y | Prathap Educational Society | Red Chillies and Pulses | Machavaram | yes | companies act | 29/06/2022 | U01100AP2022PTC122127 | 30/09/2022 | completed | Yes | Yes | 470 | Yes | 2022-05-11 |  | 705000 | Yes | Yes | Not received |  |  | yes | yes | 22/12/2024
9 | SFAC | Srikakulam | Ranastalam | Y | Prathap Educational Society | coconut | Ranastalam Women Farmers Producer Company Limited | YES | Company Act | ###### | U01110AP2021PTC119321 | 31/11/2021 | completed | Yes | Yes | 587 | applied | 2022-06-11 |  | 795000 | Yes | yes | yes |  | 50000 | Yes | Yes | 22/12/2022
10 | SFAC | Srikakulam | Ponduru | Y | Prathap Educational Society | Pulses | Ponduru Women Farmers Producer Company Limited | YES | Company Act | 31/08/21 | U01100AP2021PTC119272 | 31/11/21 | completed | Yes | Yes | 598 | applied | 2022-06-11 |  | 870000 | Yes | yes | yes |  | 50000 | Yes | Yes | 22/12/2022
11 | NABARD | Anantapur | Nijavalli, M.Venkatampalli & Malayanur (Kundurpi Mandal) | Yes | AFEC | Groundnut & Horticulture | Dharani RUPSS Ltd. | Yes | MACS Act 1995 | 16th April 2022 | AMC/ATP/DCO/2022/5097 | 14th July 2022 | 25th June 2022 | Yes | Yes | 350 | Yes | 28.09.2022 | NA | 317000 | Yes | yes | Yes |  | 317000 | Induction Done |  | 23.12.2022 | Awareness Meetings are going on in the villages and shareholders enrollment is in progress
12 | NABARD | Anantapur | Yalagalavanka, Yalagalavanka thanda, Virupapalli & Bramanapalli (Beluguppa mandal) | Yes | AFEC | Groundnut & Horticulture | Pragathi RUPSS Ltd. | Yes | MACS Act 1995 | 16th April 2022 | AMC/ATP/DCO/2022/5096 | 14th July 2022 | 25th June 2022 | Yes | Yes | 319 | No |  | NA | 190000 | Yes | In Process |  | 10th July 2022 |  | Induction Done |  | 23.12.2022 | Awareness Meetings are going on in the villages and shareholders enrollment is in progress
13 | NABARD | Anantapur | Muttala, Goridindla & Papampalli (Atmakur mandal) | Yes | AFEC | Groundnut & Horticulture | Sasyamitra RUPSS Ltd. | Yes | MACS Act 1995 | 31st March 2022 | AMC/ATP/DCO/2022/5094 | 30th June 2022 | 15th June 2022 | Yes | Yes | 236 | NA |  | NA | 208000 | Yes | In Process |  | 10th July 2022 |  | Induction Done |  | 23.12.2022 | Awareness Meetings are going on in the villages and shareholders enrollment is in progress
14 | NABARD | Chittoor | G.D.Nellore | yes | RHGBMSS | Mango and Vegetables | Lakshmi Narasimha Swamy Farmer Producer Company Ltd. | YES | Company Act | 7th April 2021 | U01119AP2O22PTC121284 | 30th June 2022 | 30th June 2022 | YES | NO | 320 | NO |  |  | 245000 | Yes | no | no | 20.07.2022 |  | Yes | YES | 23.12.2022 | Awarness Meeting conducted in villages
15 | NABARD | Chittoor | Pulicherla | yes | RHGBMSS | Mango and Vegetables | Mangalampeta Farmer Producer Company Ltd | YES | Company Act | 11th May 2022 | U01100AP2022PTC121615 | 20th August 2022 | 20th August 2022 | YES | NO | 328 | NO |  |  | 125000 | Yes | NO | NO | 20.08.2022 |  | Yes | YES | 23.12.2022 | Awarness Meeting conducted in villages
16 | NABARD | Chittoor | Yerpedu | yes | RHGBMSS | Groundnut, Vegetables & Floriculture | Mana samudram agricultura FPO company limited | YES | Company Act | 30th March 2022 | U01100AP2022PTC121220 | 25th June 2022 | 25th June 2022 | Yes | yes | 305 | Yes | Equity Grant Received 305000 | NA | 305000 | Yes | Submitted | Submitted | Equity Grant Received 305000 | NO | Yes | YES | 23.12.2022 | Awarness Meeting conducted in villages
17 | NABARD | East Godavari | Tuni | Yes | BREDS | Mango and value-added products | Farm Values Farmer Producer Company Limited | Yes | Company Act | 2022-11-05 | U01100AP2022PTC121617 | Yes | 30th August 2022 | Yes | YES | 300 | Yes | 01.11.2022 | One month back registered | 300000 | Yes | Yes | No |  |  | Yes | YES | 23.12.2022
18 | NABARD | East Godavari | Ravulapalem | Yes | BREDS | Banana | Bangaru Talli Farmers Producer Company limited | Yes | Company Act | 17-04-2022 | U01100AP2022PTC121542 | Yes | 30th August 2022 | Yes | Yes | 85 | NO |  | One month back registered | 16500 | Yes | Yes | No |  |  | Yes | YES | 23.12.2022
19 | NABARD | East Godavari | Upland mandals of the district (Tuni, Tondangi, Sankavaram, Routulapudi | Yes | BREDS | ZBNF (Vegetables, Pulses, Cashew, Horticulture Crops) other than paddy | Sri Veda Farmers Producer Company Limited | Yes | Company Act | 19-03-2022 | U01100AP2022PTC121356 | Yes | 2022-10-09 | Yes | Yes | 200 | NO |  | One month back registered | 50000 | Yes | Yes | No |  |  | Yes | YES | 23.12.2022
20 | NABARD | East Godavari | Tribal mandals of the district | Yes | BREDS | Millets & Pulses | Sri Pasidi Kanti Farmer Producer Company Limited | Yes | Company Act | 16-04-2022 | U01100AP2022PTC121575 | Yes | 30th August 2022 | Yes | Yes | 200 | NO |  | One month back registered | 150000 | Yes | Yes |  |  |  | Yes | YES | 23.12.2022
21 | NABARD | Guntur | Bollapalli | Yes | SEARCH | Chilli and Pulses | Pudamimitra FPCl | Yes | Company Act | 12.10.2022 | U01100AP2022PTC123003 |  |  | Yes | Yes | 130 | No |  |  | 130000 | Yes | No |  |  |  |  | No | 23.12.2022
22 | NABARD | Guntur | Karempudi | Yes | SEARCH | Chilli and Pulses | Gandikota Thimmanayudu Farmer Producer Company Limited | UNDER PROCESS | Company Act | 31.05.2022 | U01100AP2022PTC121842 |  |  | Yes | Yes | 302 | No |  |  | 302000 | Yes | [6 empty] | 23.12.2022
23 | NABARD | Guntur | Vatticherukuru | Yes | SEARCH | Chilli and Pulses | Bhuputhra Farmer Producer Company Limited | Yes | company Act | 06.09.2022 | U01100AP2022PTC122619 |  |  | Yes | Yes | 138 | No |  |  | 138000 | No | [6 empty] | 23.12.2022
24 | NABARD | Kadapa | Kalasapadu | 26.10.2021 | RHGBMSS | Cereals (Jowar/Bajra) | Sri Siva Sakthi armer Producers Mutally Alided Co Operative Socity Ltd | Yes | Cooperative act | 24.01.2022 | AMC/KDP/DCO/2022/2840 | Yes | 24.04.2022 | Yes | No | 304 | Yes | 05.09.2022 |  | 304000 | Yes | Yes | Yes |  | 304000 | Yes | yes | 23.12.2022
25 | NABARD | Kadapa | Porumamilla | 26.10.2021 | RHGBMSS | Cereals (Jowar/Bajra) | Sri Sai Krishna Farmer Producers Mutally Alided Co Operative Socity Ltd | Yes | Cooperative act | 24.01.2022 | AMC/KDP/DCO/2022/2841 | Yes | 24.04.2022 | yes | YES | 509 | YES | 10.08.2022 |  | 509000 | yes | Yes | Yes | 25.07.2022 | to be released | Yes | yes | 23.12.2022 | it is Pending with PMMS .The FPO Having Account in DCCB Bank
26 | NABARD | Kadapa | B Koduru | 26.10.2021 | RHGBMSS | Cereals (Jowar/Bajra) and Pulses | Sri Duggam Farmer Producers Mutally Alided Co Operative Socity Ltd | yes | company act | 11.07.2022 | U01100AP2022PTC122225 | yes | 25.09.2022 | Yes | No | 306 | Yes | 20.10.2022 |  | 306000 | yes | Yes | Yes | 25.10.2022 | 306000 | Yes | yes | 23.12.2022
27 | NABARD | Krishna | Gantasala | Yes | SEARCH | Black Gram | BHAVITHA BLACK GRAM FARMER PRODUCER CO.LTD | Yes | Company Ltd. | 28.4.2022 | U01100AP2022PTC121503 |  |  | Yes | Yes | 215 | NO |  |  | 215000 | Yes | No | No |  |  |  |  | 23.12.2022
28 | NABARD | Krishna | Ibrahimpatnam | Yes | SEARCH | Vegetables & Chilli | Ibrahimpatnam Vegetables and Chilli Farmer Producer Co.Ltd. | yes | Company Ltd. | 26.09.2022 | U01100AP2022PTC122867 |  |  | Yes | Yes | 173 | NO |  |  | 173000 | Yes | [6 empty] | 23.12.2022
29 | NABARD | Krishna | Vatsavai | Yes | SEARCH | Maize & Vegetables & Chilli | Vastavai Farmer Producer Co.Ltd. | Yes | Company Ltd. | 02.06.2022 | U01100AP2022PTC121884 |  |  | Yes | Yes | 263 | NO |  |  | 263000 | Yes | [6 empty] | 23.12.2022
30 | NABARD | Kurnool | Nandavaram Mandal | Yes | EFFORT | Onion & Chillies | Nandvaram Shrama Shakthi Farmers Producer Company Ltd | Yes | Company Ltd. | 2022-03-04 | U01100AP2022PTC120990 |  |  | yes | Yes | 305 | Yes | 16.08.2022 |  | 305000 | Yes | yes | Yes |  | 305000 |  |  | 23.12.2022
31 | NABARD | Kurnool | Tuggali Mandal | Yes | EFFORT | Pulses | Tuggali Arunodaya Farmers Producers Company Ltd | Yes | Company Ltd. | 2022-07-03 | U01100AP2022PTC120993 |  |  | yes | Yes | 306 | Yes | 16.08.2022 |  | 306000 | Yes | yes | yes |  | To be released |  |  | 23.12.2022
32 | NABARD | Kurnool | Peapully Mandal | Yes | EFFORT | Tomato | Vighnan Farmers Producer Comapny Ltd | yes | Company Ltd. | 2022-04-04 | U01100AP2022PTC121255 |  |  | Yes | Yes | 302 | Yes | 16.08.2022 |  | 302000 | Yes | Yes | yes |  | 302000 |  |  | 23.12.2022
33 | NABARD | Nellore | Podalkur, Chejerla, Kaluvoy and Rapur | Yes | ASSIST | Pulses - Black gram | Vutukuru Tribel Millets Farmers Producer Company LTD | Yes | company Ltd | 15-7-2022 | U01111AP2022PTC122277 | yes | 30/9/2022 | Yes | yes | 102 | NO |  |  | 120000 | Yes | yes | NO |  |  | Yes | Yes | 23.12.2022 | Awareness Meetings are going on in the villages and shareholders enrollment is in progress
34 | NABARD | Nellore | Udaigiri, Sitarampuram, V K Padu, Marripadu and Duttalur | Yes | ASSIST | Millets | Duttaluru Millets Farmers Producer Company LTD | Yes | company Ltd | 26-7-2022 | U01100AP2022PTC122377 | yes | 30/9/2022 | Yes | yes | 220 | NO |  |  | 220000 | Yes | yes | No |  |  | Yes | Yes | 23.12.2022 | Awareness Meetings are going on in the villages and shareholders enrollment is in progress
35 | NABARD | Nellore | Udaigiri | yes | ASSIST | Millets | KONDAPALEM MILLETS FARMERS PRODUCER COMPANY LIMITED | Yes | Company Ltd | 2022-06-05 | U01409AP2022PTC121570 | yes | 30/92022 | Yes | yes | 240 | No |  |  | 240000 | Yes | yes | no |  |  | Yes | Yes | 23.12.2022 | Awareness Meetings are going on in the villages and shareholders enrollment is in progress
36 | NABARD | Prakasam | Chimakurthy | Yes | EFFORT | Bajra, Red Gram & Green gram | Chimakurthy Abhudaya Farmers producer company limited | Yes | Company Ltd | 25/04/2022 | U01113AP2022PTC121469 |  |  | Yes | no | 300 |  |  |  | 300000 | Yes | Yes | No |  |  |  |  | 23.12.2022
37 | NABARD | Prakasam | Chinnaganjam | Yes | EFFORT | Chillies, Groundnut & Bengal Gram | Chinnaganjam Siri Farmers producer company limited | yes | Company Ltd | 2022-11-04 | U01100AP2022PTC121320 |  |  | yes | no | 300 | Yes | 26.09.2022 |  | 300000 | Yes | yes | yes |  | 300000 |  |  | 23.12.2022
38 | NABARD | Prakasam | Karamchedu | Yes | EFFORT | Chillies & Bengal Gram | Karamchedu Avani Farmers producer company limited | yes | Company Ltd | 20/4/2022 | U01100AP2022PTC121401 |  |  | yes | no | 300 |  |  |  | 300000 | Yes |  | No |  |  |  |  | 23.12.2022
39 | NABARD | Srikakulam | Tekkali, Burja | Yes | ARTS | Groundnut | Kotthammatalli producer company limited | yes | companies act | 2022-10-06 | U01110AP2022PTC121935 |  |  | Yes | after registration process will appoint Accountant | 305 | Yes | 27.09.2022 |  | 610000 | yes | Yes | Yes |  | To be released | yes |  | 23.12.2022
40 | NABARD | Srikakulam | Palakonda, Veeraghattam | Yes | ARTS | Paddy | Grama velugu farmer producer company limited | Yes | companies act | 24.05.2022 | U01100AP2022PTC121756 |  |  | Yes | after registration process will appoint Accountant | 305 | Yes | 27.09.2022 |  | 610000 | Yes | Baseline survay process completed | Yes |  | To be released | yes |  | 23.12.2022
41 | NABARD | Srikakulam | Regidi Amadalavalasa | yes | ARTS | Pulses | Prakruthi vanam farmer producer company | Yes | Companies act | 2022-04-03 | U01100AP2022PTC121139 |  |  | Yes | appointed Accountant | 305 | Yes | 27.09.2022 |  | 610000 | Yes | Baseline survay process completed | Yes |  | 610000 | yes |  | 23.12.2022
42 | NABARD | Visakhapatnam | Chintapalli, GK Veedhi | Yes | BREDS | Rajma | Sugamana Farmer Producer Company Limited | Yes | Company Act | 20/04/2022 | U01409AP2022PTC121413 | Yes |  | YES | YES | 30 | NO |  |  | 30000 | Yes | [6 empty] | 23.12.2022
43 | NABARD | Visakhapatnam | GK Veedhi | Yes | BREDS | Turmeric/ Coffee | Aruna Tara Farmer Producer Company Limited | Yes | Company Act | 2022-01-03 | U01409AP2022PTC120998 | Yes |  | YES | YES | 30 | NO |  |  | 30000 | Yes | [6 empty] | 23.12.2022
44 | NABARD | Visakhapatnam | Araku, Dumbriguda | Yes | BREDS | Millets/ turmeric/coffee | Sagara Mouli Farmer Producer Company Limited | Yes | Company Act | 2022-04-04 | U01409AP2022PTC121283 | Yes |  | YES | YES | 32 | NO |  |  | 32000 | [7 empty] | 23.12.2022
45 | NABARD | Vizianagaram | Bobbili, Ramabhadrapuram, Badangi, Balijipeta and Seetanagaram | Yes | BREDS | Maize/Pulses/Fruits/vegetables/Sugarcane | Swarna Dhara Farmer Producer Company Limited | Yes | Company Act | 17/03/2022 | U01409AP2022PTC121380 | Yes | 30-08-2022 | Yes | Yes | 147 | No |  | In process | 112000 | Yes | Yes |  |  |  | Yes | Yes | 23.12.2022 | Awareness Meetings are going on in the villages and shareholders enrollment is in progress
46 | NABARD | Vizianagaram | Gajapatinagaram, Bondapalli, Dattirajeru and Mentada | Yes | BREDS | Maize/Pulses/Fruits/vegetables/Sugarcane | Veda Vahini farmer Producer Company limited | Yes | Company Act | 15/03/2022 | U01100AP2022PTC121056 | Yes | 30-08-2022 | Yes | Yes | 119 | No |  | In process | 143000 | Yes | Yes |  |  |  | Yes | Yes | 23.12.2022
47 | NABARD | Vizianagaram | Vizianagaram rural, Denkada, Pusapatirega and Bhogapuram | Yes | BREDS | fruits, Veg, Flowers, Coconut | Paiditallamma Farmer Producer Company Limited | Yes | Company Act | 15/03/2022 | U01100AP2022PTC121053 | Yes | 30-08-2022 | Yes | Yes | 280 | No |  | In process | 280500 | Yes | Yes |  |  |  | Yes | Yes | 23.12.2022
48 | NABARD | West Godavari | T. Narasapuram | Yes | ASSIST | Lemon / Coconut | In process | Under Process | Company act |  |  |  |  | Yes | Yes | 38 | [8 empty] | NA | Yes | In process |  | Awareness Meetings are going on in the villages and shareholders enrollment is in progress
49 | NABARD | West Godavari | Jangareddygudem | Yes | ASSIST | Lemon / Coconut | Ammapalem farmers producer company limited | Yes | Company act | 2022-10-06 | U01100AP2022PTC121925 | Yes | 20-09-2022 | Yes | Yes | 300 | No |  | In Process | 6,00,000 | Yes | Yes | No | 28-01-2023 | NA | Yes | Yes | 27-01-2023 | Management cost request for Sanction praposal submitted
| NABARD | West Godavari | Koyyelagudem | Yes | ASSIST | Lemon / Vegetables Horticulture | Bogalingeswara farmers producer company limited | Yes | Company act | 15-04-2022 | U01100AP2022PTC121363 | Yes | 18-09-2022 | Yes | Yes | 300 | Yes | 20-12-2022 |  | 3,00,000 | Yes | Yes | No |  | NA | Yes | Yes | 27-01-2023 | GST Recived and Management cost request for Sanction praposal submitted
51 | SFAC | Krishna | Penamaluru | Pending | Narayana Seva Samithi
52 | SFAC | Krishna | Pedaparupudi | Pending | Narayana Seva Samithi
53 | SFAC | Krishna | chellapalli | Pending | Narayana Seva Samithi
54 | SFAC | Eluru | Chatrai | Approved | Narayana Seva Samithi | Maize
55 | SFAC | Eluru | Unguturu | Approved | Narayana Seva Samithi | Paddy
56 | SFAC | East Godavari | Undrajvaram | Approved | Narayana Seva Samithi
57 | SFAC | West Godavari | Tdepalligudem | Pending | Narayana Seva Samithi | Cocoa
58 | SFAC | Kakinada | Pittapuram | Approved | Narayana Seva Samithi | Vegetables
59 | SFAC | Kakinada | Kirlampadu | Approved | Narayana Seva Samithi | Cashewnut ad Banana
60 | SFAC | Kakinada | Pratipadu | Approved | Narayana Seva Samithi | Pulses and Vegetables
61 | SFAC | YSR Kadapa | Chennur | N | Simhapuri Vydya Seva Samithi | Betel leaf
62 | SFAC | YSR Kadapa | Rajupalem | N | Simhapuri Vydya Seva Samithi | Pulses and cotton
63 | SFAC | Annamaya | Chinnamandem | Y | Simhapuri Vydya Seva Samithi
64 | SFAC | Tirupathi | KVB Puram | Y | Simhapuri Vydya Seva Samithi | Vegetables and Ground nut
65 | SFAC | Tirupathi | Thottambedu | Y | Simhapuri Vydya Seva Samithi | Vegetables and Ground nut
66 | SFAC | Chittor | Vedurukuppam | Y | Simhapuri Vydya Seva Samithi | Mango and Vegetables
67 | SFAC | Sri Pottisriramulu Nellore | Buchireddy palem | Y | Simhapuri Vydya Seva Samithi | Paddy
68 | SFAC | Sri Pottisriramulu Nellore | Bogole | Y | Simhapuri Vydya Seva Samithi | Ground nut
69 | SFAC | Sri Pottisriramulu Nellore | Vinjamuru | Y | Simhapuri Vydya Seva Samithi | Turmeric
70 | SFAC | Sri Pottisriramulu Nellore | Vidavaluru | Y | Simhapuri Vydya Seva Samithi | Paddy

## 2022-23
S.No | Name of Implementing Agency | Name of District | Name of Block | DMC approval Status (Y/N) | Name of CBBO allocated the block and their contact details | Focus Crop | Name of FPO | FPO registered (Y/N) | FPO registered under Act ( Company Act / Cooperative Act / Others please specify) | Date of FPO Registration | Registration No. | 90 days from the date of registration or 10.11.2021 | Date by which the FPO will achive 300 members | Appointmnet of CEO (Yes/ No) | Appointment of Accountant (Yes/ No) | Sl No | No. of Farmer members | whether Applied for Equity Grant Yes/No | If Yes Date on Which Applied fo EG | If No State Reason | Equity Amount (in Rs.) | Whether Bank account opened | Business Plan preparation (Yes/ No) | Sanction of equity grant (Yes/ No) | If No, date by which the CBBO will submit the equity grant application | Equity Grant Received (Rs lakh) | Training Of CEO Yes/No | Training Of BOD Yes/No
1 | NABARD | Bapatla |  | Pending | ASSIST
2 | NABARD | Eluru | Chintalapudi | Yes | ASSIST; 9701942715 | Acid lime and Coconut | In process | NO | Company act | NA |  |  |  | Yes | Yes |  | 50 | [9 empty] | Yes | Under process
3 | NAFED | Eluru | T.Narsapuram | Yes | ACCESS Development Services - 9885735563 | Coconut & Coco | In process | NO | Company act | NA |  |  |  | No | No
4 | NAFED | Eluru | Lingapalem | Yes | ACCESS Development Services - 9885735563 | Chilli & Maize | In process | NO | Company act | NA |  |  |  | No | No
5 | NAFED | Eluru | Chintalapudi | Yes | ACCESS Development Services - 9885735563 | Coconut & Coco | In process | NO | Company act | NA |  |  |  | No | No
6 | NAFED | Eluru | Jeelugumilli | Yes | ACCESS Development Services - 9885735563 | Groundnut & Maize | In process | NO | Company act | NA |  |  |  | No | No
7 | NAFED | Eluru | Buttayigudem | Yes | ACCESS Development Services - 9885735563 | Cashew & Maize | In process | NO | Company act | NA |  |  |  | No | No
8 | NABARD | Alluri Sitharama Raju | Dumbiriguda(Aruku vally) | Approved | Action in Rural Technology and Service (ARTS) | Coffee, turmeric, Black pepper & other Agri. Hort.produce
9 | NABARD | Alluri Sitharama Raju | Rampachodavaram | Approved | Action in Rural Technology and Service (ARTS) | Cashew, turmeric and other Agri. Hort.produce
10 | NABARD | Alluri Sitharama Raju | G Madugula | Approved | ICAR-Indian Institute of Millet Research (IIMR), Hyderabad | Turmeric and other Agri. Hort.produce
11 | NABARD | Alluri Sitharama Raju | Hukkumpeta | Approved | ICAR-Indian Institute of Millet Research (IIMR), Hyderabad | Turmeric and other Agri. Hort.produce
12 | NABARD | Anakapalli | Payakarao peta | Approved | ICAR-Indian Institute of Millet Research (IIMR), Hyderabad | Betlevine & vegitables
13 | NABARD | Anakapalli | Nathavaram | Approved | ICAR-Indian Institute of Millet Research (IIMR), Hyderabad | Chashew, Pulses
14 | NABARD | Ananthapuramu | Kalyandurgam | Approved | Action Fraterna Ecology Centre | Kalyandurgam
15 | NABARD | Annamayya | Gurramkonda | Approved | Andhra Pradesh Mahila Abhivruddhi Society, Hyderabad ( APMAS) | Tomato | Gurramkonda Farmers producer company Limited |  | Company Act
16 | NABARD | Annamayya | Lakkireddypalli | Approved | Rayalaseema Harijana Girirjana Backward Minorities Seva Samajam (RHGBMSS) | Ground nut & Pulses | Lakkireddy Palli Farmer Producer Company Ltd | Yes | Company Act | 14-12-2022 | U01100AP2022PTC123574 |  | 20.03.2023 | Yes | No |  | 205 | No |  |  |  |  | No | No |  |  | YES | YES
17 | NABARD | Annamayya | Veeraballi | Approved | Rayalaseema Harijana Girirjana Backward Minorities Seva Samajam (RHGBMSS) | Mango | Sri Lakshmi Veeraballi Mango Farmer Prodcuer Company Ltd. | Yes | Company Act | 28.12.2022 | U01100AP2022PTC123705 |  | 25.03.2023 | Yes | No |  | 110 | no |  |  |  |  | no | No |  |  | NO | YES
18 | NABARD | Bapatla |  | Pending | ASSIST
19 | NABARD | Eluru | Chintalapudi | Approved | ASSIST | Acid lime & Coconut
20 | NABARD | Bapatla | Yeddanapudi | Approved | SEARCH | Chilly, Pulses
21 | NABARD | Bapatla | Inkollu | Approved | SEARCH | Chilly, Pulses
22 | NABARD | Chittoor | Thavanampalle | Approved | Andhra Pradesh Mahila Abhivruddhi Society, Hyderabad ( APMAS) | Mango | Thavanampalle Farmers producer Company Limited |  | Company Act
23 | NABARD | Chittoor | Gudipala | Approved | Andhra Pradesh Mahila Abhivruddhi Society, Hyderabad ( APMAS) | Vegetables | Real Gudipala Farmers producer company Limited |  | Company Act
24 | NABARD | Chittoor | Chowdepalle | Approved | Andhra Pradesh Mahila Abhivruddhi Society, Hyderabad ( APMAS) | Tomato | Sri Boyakonda Gangamma Farmers producer Company Limited |  | Company Act
25 | NABARD | East Godavari | Rajahmundry Rural | Approved | BREDS, Srikakulam | Vegetables
26 | NABARD | East Godavari | Nidadavole | Approved | National Agro Foundation, Research and Development Centre, Chennai | Cashew |  | N | /
27 | NABARD | Guntur | Ponnur | Approved | ASSIST | Pulses, Chilli
28 | NABARD | Eluru | Rajahmundry Rural | Approved | BREDS, Srikakulam | Groundnut, Maize, Cashew
29 | NABARD | Guntur | Pedanandipadu | Approved | ASSIST | Chilli, Pulses
30 | NABARD | Sri Potti Sriramulu Nellore | Chejerla | Approved | ASSIST | Vegetables, Acid Lime | SRI PENUSILA LAKSHMINARASIMHA UDYANA RYTHU SANGHAM |  | Company Act
31 | NABARD | Kakinada | Kotananduru | Approved | BREDS, Srikakulam | Pulses
32 | NABARD | Kakinada | Gollaprolu | Approved | BREDS, Srikakulam | Organic vegetables
33 | NABARD | Konaseema | Athreyapuram | Approved | National Agro Foundation, Research and Development Centre, Chennai | Banana, Flowers | Atreyapuram Farmer Producer Company Limited | N | Companies Act, 2013
34 | NABARD | Konaseema | Alamuru | Approved | National Agro Foundation, Research and Development Centre, Chennai | Coconut, Banana | Alamuru Farmer Producer Company Limited | N | Companies Act, 2013
35 | NABARD | Krishna | Movva | Approved | EFFORT, Prakasham | Black Gram
36 | NABARD | Krishna | Guduru | Approved | EFFORT, Prakasham | Jasmine
37 | NABARD | Kurnool | Halaharvi | Approved | EFFORT, Prakasham | Bengalgram, Groundnut & Cotton | Halaharvi Annadatha Farmer Producer Company Limited |  | Company Act
38 | NABARD | Kurnool | Chippagiri | Approved | EFFORT, Prakasham | Chilli & Cotton
39 | NABARD | Nandyal | Jupadubunglow | Approved | EFFORT, Prakasham | Maize & Cotton
40 | NABARD | Nandyal | Nandikotkur | Approved | EFFORT, Prakasham | Chilli
41 | NABARD | NTR | Jaggaiahpeta | Approved | SEARCH | Maize & Vegetables
42 | NABARD | NTR | G Konduru | Approved | SEARCH | Chilli & Vegetables
43 | NABARD | NTR | Mylavaram | Approved | SEARCH | Horticulture crops
44 | NABARD | Palnadu | Savalyapuram | Approved | SEARCH | Pulses, Chilli
45 | NABARD | Palnadu | Nadendla | Approved | SEARCH | Chilli, Pulses
46 | NABARD | Parvathipuram Manyam | Makkuva | Approved | Action in Rural Technology and Service (ARTS) | Millets, Pulses & Banana
47 | NABARD | Parvathipuram Manyam | Salur | Approved | Action in Rural Technology and Service (ARTS) | Millets, Tamarind & Cashew
48 | NABARD | Parvathipuram Manyam | Gummalakshmipuram | Approved | Action in Rural Technology and Service (ARTS) | Tamarind, Hill Blooms, custred apple, Tamarind & Cashew
49 | NABARD | Prakasam | Kondapi | Approved | EFFORT, Prakasham | Redgram & Bengalgram
50 | NABARD | Prakasam | Santha Nuthalapadu | Approved | EFFORT, Prakasham | Redgram & Bengalgram
51 | NABARD | Prakasam | Talluru | Approved | EFFORT, Prakasham | Sweet Orange & Guava & Papaya | Thalluru Ganga Sai Farmer Producer Company Limited |  | Company Act
52 | NABARD | Sri Potti Sriramulu Nellore | Jaladanki | Approved | ASSIST | Vegetables, Mango
53 | NABARD | Eluru | Dwarakatirumala | Yes | ASSIST; 9701942715 | ACID LIME and Coconut, Cocoa | In process | NO | Company act | NA |  |  |  | Yes | Yes |  | 70 | [9 empty] | Yes | No
54 | NABARD | Sri Sathya Sai | Dharmavaram | Approved | Action Fraterna Ecology Centre | Groundnut, Redgram & Horsegram
55 | NABARD | Srikakulam | Ponduru | Approved | Action in Rural Technology and Service (ARTS) | Groundnut & Maize
56 | NABARD | Srikakulam | Nandigam | Approved | Action in Rural Technology and Service (ARTS) | Groundnut & Maize
57 | NABARD | Tirupati | Srikalahasti | Approved | Rayalaseema Harijana Girirjana Backward Minorities Seva Samajam (RHGBMSS) | Vegetables, Redgram & Groundnut | FPO Was Sanctioned ,but to be changed
58 | NABARD | Visakhapatnam | Padmanabham | Approved | BREDS, Srikakulam | Agri & Horti crops
59 | NABARD | Visakhapatnam | Anandapuram | Approved | BREDS, Srikakulam | Agri & Horti crops
60 | NABARD | Vizianagaram | Jami | Approved | BREDS, Srikakulam | Horticulture crops
61 | NABARD | Vizianagaram | Mentada | Approved | BREDS, Srikakulam | Horticulture crops
62 | NABARD | Vizianagaram | Vepada | Approved | BREDS, Srikakulam | Sesamum
63 | NABARD | Vizianagaram | Srungavarapukota | Approved | ICAR-Indian Institute of Millet Research (IIMR), Hyderabad | Millets
64 | NABARD | West Godavari | Narasapuram | APPROVED | National Agro Foundation, Research and Development Centre, Chennai
65 | NABARD | YSR Kadapa | Duvvur | Approved | Rayalaseema Harijana Girirjana Backward Minorities Seva Samajam (RHGBMSS) | Turmric & Maize | Sri Veerabrahmendra FPO | Yes | company act | 29.12.2022 | U01100AP2022PTC123733 | 20.03.2023 | 20.03.2023 | Yes | NO |  | 150 | [10 empty] | YES
66 | NABARD | YSR Kadapa | Muddanur | Approved | Rayalaseema Harijana Girirjana Backward Minorities Seva Samajam (RHGBMSS) | Citrus/Sweet Orange | In process | no | company act | under proccess |  |  |  | UNDER PROCESS | NO |  | 25
67 | SFAC | YSR Kadapa | Brahmamgarimattam | Yes | Ekalavya Foundation | Cereals | Brahmamgarimattam Framers Producer Company Limited | Yes | Company Act | 16.12.2022 | U01100AP2022PTC123595. | 16.03.2023 | 16.03.2023 | Yes | No
68 | SFAC | Alluri Seetharama Raju | Paderu | Yes | Ekalavya Foundation | Coffee, Turmeric, Pepper | In Process | No
69 | SFAC | Alluri Seetharama Raju | Hukumpeta | Yes | Ekalavya Foundation | Turmeric, Pepper | In Process | No
70 | SFAC | Alluri Seetharama Raju | G.Madugula | Yes | Ekalavya Foundation | Coffee, Turmeric, Pepper | In Process | No
71 | SFAC | Kurnool | Aspari | Pending | Krushijeevan Agro Farmers Producer Company Ltd
72 | SFAC | Kurnool | Chippagiri | Pending | Krushijeevan Agro Farmers Producer Company Ltd
73 | SFAC | Kurnool | Devanakonda | Pending | Krushijeevan Agro Farmers Producer Company Ltd
74 | SFAC | Kurnool | Halaharvi | Pending | Krushijeevan Agro Farmers Producer Company Ltd
75 | SFAC | Tirupathi | Sathyavedu | Yes | National Agro Foundation, Research and Development Centre, Chennai | Mango, Groundnut | Sathyavedu Farmer Producer Company Limited | No | Company Act
76 | SFAC | Alluri Seetha Ramaraju | Gangavaram | Yes | National Agro Foundation, Research and Development Centre, Chennai | Cashew Nut | Gangavaram Farmer Producer Company Limited | Yes | Company Act | 2022-05-12 | U01100AP2022PTC123444 | 5/3/0202 | 2023-05-03 | Yes | Yes |  | 200 |  |  |  |  | No | No | No |  | No | No | No
77 | SFAC | Kakinada | Kakinada Rural | Yes | National Agro Foundation, Research and Development Centre, Chennai | Vegetables |  | No | Company Act
78 | SFAC | West Godavari | Penugonda | Yes | National Agro Foundation, Research and Development Centre, Chennai | Vegetables | Penugonda Farmer Producer Company Limited | No | Company Act
79 | SFAC | West Godavari | Achanta | Yes | National Agro Foundation, Research and Development Centre, Chennai | Vegetables | Achanta Farmer Producer Company Limited | No | Company Act
80 | NCDC | Alluri Sitaramaraju | Chinthapalli | No | ARTS, Srikakulam Sh. Sanyasi Rao, Director Mob: 9440630945 | As per DMC Recemmendation/ODOP | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
81 | NCDC |  | Chintoor | No |  | As per DMC Recemmendation/ODOP | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
82 | NCDC |  | Devipatnam | No |  | As per DMC Recemmendation/ODOP | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
83 | NCDC |  | G.K Veedhi | No |  | As per DMC Recemmendation/ODOP | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
84 | NCDC | Anakapalli | Atchutapuram | No | GO Aadharita Prakruti Vyavasayadarula MACS Sh.Bharath Verma, CEO Mob: 9951282288 | As per DMC Recemmendation/ODOP | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
85 | NCDC |  | Butchiahpeta | No |  | As per DMC Recemmendation/ODOP | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
86 | NCDC |  | Cheedikada | No |  | As per DMC Recemmendation/ODOP | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
87 | NCDC |  | Chodavaram | No |  | As per DMC Recemmendation/ODOP | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
88 | NCDC | Vizianagaram | Bhogapuram | No | ARTS, Srikakulam Sh. Sanyasi Rao, Director Mob: 9440630945 | As per DMC Recemmendation/ODOP | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
89 | NCDC |  | Bobbili | No |  | As per DMC Recemmendation/ODOP | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
90 | NCDC |  | Bondapalli | No |  | As per DMC Recemmendation/ODOP | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
91 | NCDC |  | Chepurupalli | No |  | As per DMC Recemmendation/ODOP | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -